## Sheet1
NBCC TRON 2024 WBS
PRODUCTION TRACKER
DELIVERABLES | Design | Build | User Inputs | Output | Game State | Data Transfer | Test Client and Server | [6 empty] | DELIVERY
VIDEO CONCEPTS | [10 empty] | Client | Server | Tested Run
01 Game Design | [13 empty] | DONE
| DONE | DONE
02 Client | [13 empty] | DONE
| DONE | DONE | DONE | DONE | DONE | DONE | DONE
03 Server | [13 empty] | DONE
|  | DONE | DONE | DONE | DONE | DONE | DONE
04 Design Data Structure | [13 empty] | DONE
|  |  | DONE | DONE | DONE | DONE | DONE
05 Gameplay | [13 empty] | DONE
|  |  | DONE | DONE | DONE | DONE | DONE
|  |  | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11
01 Game Design | 1.1 Rule Game Play | 3 hours | 2024-03-04: DONE
DONE
DONE
| 1.2 Number Players/ Attributes | 1 hour | 2024-03-06: DONE
DONE
DONE
| 1.3 Set Up IDE | 2 hours | 2024-03-07: DONE
DONE
DONE
02 Client | 2.1 Design UI | 4 hours | 2024-03-08: DONE
DONE
| 2.2 Game lobby | 8 hours | 2024-03-11: DONE
| 2.2 Game Layout | 2 hours
DONE
| 2.2.1 Create Board | 1 hour
DONE
| 2.2.2 Player Object | 3 hours
DONE
| 2.2.3 Control Player | 3 hours
DONE
| 2.2.4 Add other players | 3 hours
DONE
| 2.2.5 Game State | 3 hours
DONE
| 2.2.6 Test Game | 6 hours | 2024-03-25: DONE
| 3.1 Research Possible Servers (JAVA or JS) | 3 hours | 2024-03-08: DONE
03 Server | 3.2 Setup Server | 2 hours | 2024-03-11: DONE
| 3.1.1 Design Game Data Structure | 2 hours | 2024-03-15: DONE
| 3.1.2 Implement Data Transfer Strategies | 4 hours | 2024-03-16: DONE
| 3.1.3 Test Transfer data between Client and Server | 2 hours | 2024-03-19: DONE
| 3.1.3 Update Based on Transfer Data Test | 3 hours | 2024-03-21: DONE
| 3.1.4 Update Client Outputs | 4 hours | 2024-03-24: DONE
04 Gameplay | 4.1 Test Multiple Players | 6 hours | 2024-03-30: DONE
DONE
DONE
| 4.2 Adjusting | 6 hours | 2024-04-02: DONE
DONE
DONE
05 Polishing | 5.1 Debuging | 4 hours
DONE
DONE
06 Delevery | 6.1 Executable file | 4 hours | 2024-04-09: DONE
DONE
Total Hour
DHUVIT | 40
RENZO | 42
WARIN | 45